## Sheet1
Backlog Worksheet
This sheet has to be filled while doing "Create Product Backlog" task in the Initial Envisioning Phase.
The Product backlog worksheet contains a list of features/requirements that the business would want to implement in an application. This worksheet would continue to exist from the beginning to the end of the project. The Product Owner maintains it by adding, modifying, removing any of the items listed there. They can also change the priority of the items so long as they are not being worked by the team in the ongoing Sprint. Most of the re-ordering would happen just before the Sprint Planning meeting. To ensure this kind of continuous update, this worksheet could be re-visited during periodic intervals once during the release elaboration Phase and thereafter during the project execution. The changes to the Product backlog could be triggered from several sources in terms of inclusion of new features / bugs/ known issues based on the stakeholder requests and the effort, schedule for the same would also be re-visited in the product backlog worksheet. Fill the following fields in the product backlog worksheet for each feature.
User Story ID | <Provide unique ID for each User story>
User Story Name | <Provide the theme/name of the User story or a high level requirement>
Eg: User login
Registration
Mail notification
User Story Role | < Provide who would be end User of the User story>.
Details of who would use that functionality
Eg:End User
Admin
Teacher
Conference attendee
User Story Details | <Provide description of what the User want>
Provide details on "As a/an" particular user what the user wants.
Eg: As a conference attendee, I want to be able to register online
Acceptance criteria | <Specify the Acceptance criteria>
Acceptance criteria define the boundaries of a user story, and are used to confirm when a story is completed and working as intended.
So for the above example, the acceptance criteria could include:
A user cannot submit a form without completing all the mandatory fields
Information from the form is stored in the registrations database.
Sprint | Sprint in which the user story is planned to completed. Select it from the drop down. Story Point is given in Fibonacci series of upto 21. For any User story if the estimation goes beyond 21, then the user story has to be broken down.
Story point | A story point is a metric used in agile project management and development to determine (or estimate) the difficulty of implementing a given story.
Select the story point that will be assigned to the user story from the drop down (in Fibonacci series) during the sprint planning meeting while estimating an user story.
Done | Yes/No field, that can be selected from drop down based on an user is completed or not
Added in Sprint | Provide sprint number when the particular User Story was handled
Closed in sprint | Provide sprint number when the particular User Story was completed
Actual Story Points | Actual story point burned for an user story while developing. Select from the drop down (in Fibonacci series)

## Sheet2
Product Backlog <Food Delivery App>
Project ID: <Batch code/project id> C3: Protected Controlled Copy
Done
User Story Id | User Story Name | User Story Role | User Story Details | Acceptance criteria | Sprint | Story Point | Done | Added in Sprint | Closed in sprint | Actual Story Points
1 | Registration or Sign Up | Customer & Restaurant | both user and customer have to create the acoount. | All fields need to be filled with correct input | sprint 1
2 | User Account | Customer | as user should have access to his account he can select different food | customer can access this by mobile number and verification through otp | sprint 1
3 | Restaurant account | restaurant | restaurant have to update there dishes on there account so that user can see | All mandatory fields need to be filled | Sprint 2
4 | Payment | Customer | payment mode can be anything online or cod | Payment is important as unitll payment mode is not selected customer can't proceed if its cod then payment is after delivery | Sprint 2
5 | delivery agent | restaurant | this can be accessed by both user can restaurant so that tracking get possible | this works with restaurant | Sprint 2
6 | Get Customer Details | Customer | as customer able to see order history and payment information then | Need to enter correct customer account number | Sprint 2
7 | Get Restaurant Account Details | Customer | as restaurant can see there dishes upadte them see delivery agents , also see payment mode. | details of account can be fetch only by restaurant and view by user or customer | Sprint 1
8 | View different Restaurants Food | Customer | as customer can see different restaurant food | this is under the restaurant account | Sprint 1
9 | Feedback | Customer | as rating is very important so that people get know and have information about the food and restaurant | both sender and reciver account should be valid and the amount to be transferred by sender should fall under bank balance | Sprint 2
10 | Feedback for delivery agent | customer | this is for that a delivery agent don't miss behave and don’t cheat | optional as customer intrested or not | Sprint 2